## Projects
Communication History
School No | School Name | Region Name | iTWOcx Funding Package | Bundle ID | PDC Engaged | Contractor Engaged | Registered Building Surveyor | Design Complete | Construction Complete | Admin Completion | DLP Complete | Final Closure | TOTAL Approved FUNDING ($) | Contingency Amount | Variations | Defects Outstanding (Y/N) | Status / Commentary | Last week | Week before | Week before | Week before
8889 | Albert Park College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  |  |  | 2024-06-14 |  |  |  | 94279.63 | 94279.63
Ramp 1
Ramp 2
Ramp 3
1 | Alberton Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  |  |  | 2024-06-26 |  |  |  | 1000 | 1000
8874 | Alkira Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | [6 empty] | 96920.14 | 96920.14 |  |  | Works completed with CFI issued 11/12/2025 with documentation, sign off and handover expected Janaury 2026.
5287 | Altona Green Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects | [7 empty] | 103343.4 | 103343.4 |  |  | Hum 1:1 Defects with handrails require 1000mm width. January 2027 Final sign off by RBS required - modifications to the handrail required. LIkely next week Ramps accessible before start of school term 29/01 - CFI achieved, school signoff to be scheduled with PDC (targeting Mon 2 Feb) 05/02 - Outstanding defects. HUM to close workflow 12/02 - Outstanding defects, no progress. 26/02 - Defect rectification on site from tmr
4931 | Altona North Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects | [7 empty] | 152217.98 | 152217.98 |  |  | Hum 1:1 Inspection failed due to changer of foundation by Hum. January 2027 Ramp 3 - planter box to be provided Ramp 2 - Gate issues. measurement provided to manufacturer. LIkely won't be an issue with the CFI Ramps in use 29/01 - Louise said all outstanding issues have a way forward (handrail clearance been re-measured, break in handrail on inner bend, purchase of planter boxes (school acceptance to be sought prior to purchse, cyclone gate installation and design with lower level clarified. Gate install end Feb, other mods done prior. HUM to provide program. 5/02 - Waiting for shop drawings from supplier, wants to get that approved by school first. Handrails next week. Ashphalt rectification after the fence. 12/02 - No progress Ramp 2, still waiting on shop drawing. Little defects remaining, nothing done yet. 26/02 - Moddex visiting tmr, Awaiting confirmation of dates for gate install (tmr)
800 | Ararat Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  |  |  | 2025-10-20 |  |  |  | 154851.13 | 154851.13
4848 | Ardeer Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  |  |  | 2024-06-04 |  |  |  | 1175 | 1175
8777 | Bacchus Marsh College | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  |  |  | 2025-10-29 |  |  |  | 378381.16 | 378381.16
8466 | Bairnsdale Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd | Pattersons | [6 empty] | 495400.36 | 495400.36 |  |  | RBS final inspection identified defects at Ramps 3, 5, 16 and 20. Ramp 5 & 16 to be rectified 28/01 - Inspection done but BS won't issue CFI - waiting on payment for additional inspections (in discussion with Pattersons & Spaces). Defects still remain (no ETA yet) 4/02 - No change. Pattersons won't pay BS. 10% construction value is still being held by PDC. (About 5 or 6 additional inspections done, BS wants to be paid for this). 4/03 - Still awaiting Pattersons to advise of delivery (from Alex) to fix defects. Andy and Dileep attended this site (see email)
5560 | Barton Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa |  |  | 2025-12-12 |  |  |  | 351958.5 | 351958.5
4803 | Beaumaris North Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | [6 empty] | 200486.07 | 200486.07 |  |  | CFI Paperwork expect Tues/Wed 21 Jan. RBS has now been paid Defects inspection to be scheduled next week GRN demob from site
319 | Bellbrae Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 16 | JMA Architects | [7 empty] | 647.5 | 647.5
7603 | Berwick Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Hum | [6 empty] | 436050.96 | 436050.96 |  |  | Agreed to get out RBS for CFI of all completed ramps asap to reduce distruption to school, ramp R4 & likely R1 won't be done in time. Recently new Principal & FM. Ramp 1: Completion 04.02.26 • Landing poured yesterday • Rubber ramp to be measured today (23.01.26) lead time 5-7 days manufacture. 4 Feb forecast • Install of temp ramp & handrail, completed 29.01.2026 to allow access. Final Ramp 4: ON HOLD. awaiting engineers' advice 29/01. Balustrade been replaced but now all ramp is flexing & could be unsafe, struc engineer to inspect 23/01. Handrails to be removed Ramp 7: Completion 29.01.2026 • Asphalts poured, Bollard footings poured, Install of bollards & line marking - Wednesday 28.01.2026 (now 2nd Feb) Ramp 9: Completion 09.02.26 Carpentry to be book in conjunction with ramps 1 & 7 as it's a day visit. Ramp 10: Completion 09.02.26 Carpentry to be book in conjunction with ramps 1 & 7 as it's a day visit. Final Inspection on 10 Feb. 5/02 - Works finished except R4 end next week 13/02 26/02 - Carpentry done R1,4,7,10. R4 handrails removed and made good, R1 rubber done. R9 new issues. R10 Done. Awaiting updated modex shop drawings. Maybe mid 15/03.
7670 | Buckley Park College | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects | Pirotta | [6 empty] | 315891.55 | 315891.55 |  |  | Pirotta 1:1 Ramp 17 remaining handrails by Moddex by 23/01/2026 21/01 - Ramp 17 frame to be installed this week. Decking and cladding next week and nosing/handrails the following week. target completion 30 Jan. Final Inspection Jan 30 29/01 - Slipped by one week Ramp 17 (hot weather), ramp to complete this week, nosing next week. 5/02 - Cleanup next week, signoff next week. 26/02 - Seeking signoff on Mon 2/03
5383 | Canadian Lead Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects | Pirotta | [6 empty] | 414221.64 | 414221.64 |  |  | Pirotta 1:1 Ramp 3 23/01/2026 and Ramps 1 and 2 by 27th February 2026. 21/01 - Ramp 3 will commence 27-Janby Moddex. Ramp 1 & 2 fabrication on-going. Potential delay for Ramp 1 29/01 - Ramp 3 starting today (hot weather delay). R1&2 shop design awaiting from Moddex, maybe Building Permit amendment. Forecast date 27/2 is likely at risk with R1&2. 5/02 - Cameron/David/Grymbos plan to submit BP amendment this week. Anticipate 2 weeks for approval, then commence onsite (say 1 after). In parallel moddex manufacture. Say 2 weeks construct, 1 week moddex & clean up (eta 20/03 for complete), CFI signoff probably week after. 12/02 - Ramp 3 frame approved, next week concrete, nosing & temp fence. R1&2 still in shop drawings, manufacturing yet to start, building permit mod required. 26/02 - R3 delayed (probably 1week work). R1&2 Amended BP not achieved, need update from Pirotta, last PC date 20/3 very unlikely.
2897 | Carnegie Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  |  |  | 2025-08-12 |  |  |  | 10000 | 10000
5435 | Carwatha College P-12 | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Bowdens | [6 empty] | 751300 | 751300 |  |  | 27/01: Ramp 12 to be maintained. non-DDA accessible ramp sign, removable bollards and map showing alternate DDA access route to be installed. Transfer cost to Ramp 18 - school :endorsed 29/01 - Principal sent recent email, please review. Letter of Completion received from RBS (to Tim Meldrum). Need school endorsement of re-design of Ramp 18 (school entrance access). 5/02 - Currently doing 17 forecasting completion 9/2, Ramp 18 still needs approval from VSBA (Dileep awaiting final costs (action with JMA). Carpark disruption required for R18 construction, builder wants help/support from school. R24 needs approval (coupled with ramp 18 proximity), will be constructed together. 26/02 - Costings need reviews, much much higher than previous ramps done.
3341 | Chelsea Heights Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots | [6 empty] | 146792.44 | 146792.44 |  |  | DLP Period
2061 | Chilwell Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  |  |  | 2025-08-06 |  |  |  | 191005.5 | 191005.5
4384 | Clayton South Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 18 | JMA Architects |  |  |  | 2024-07-09 |  |  |  | 2000 | 2000
3664 | Clyde Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa |  |  | 2025-12-12 |  |  |  | 47227.02 | 47227.02
5090 | Coburn Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects | Hum | [6 empty] | 692825.98 | 692825.98 |  |  | Hum 1:1 Ramp 12 5/01/2026 but likely February PCC. R10 CFI received R12 - demo complete 29/01 - demo delayed (done yesterday). Concrete pour for today. Forecasting all done 20/2 2/02 - Louise advised of permit issue causing delay to concrete and carpentry. awaiting update 5/02 - Concrete pour forecast 14/02, hopefully all complete this same week. School unhappy with work during term - want weekday only. 12/02 - 27th forecast completion. Demo and concrete works not to happy during the week 26/02 - Demo complete, concrete pour tmr. 11/03 forecast completion, proposing walkthru on same day with school
8864 | Colac Secondary College | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  |  |  | 2025-07-15 |  |  |  | 135466.6 | 135466.6
5510 | Cranbourne Carlisle Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | [6 empty] | 28183 | 28183
5518 | Cranbourne East Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa |  |  | 2025-12-12 |  |  |  | 119004.62 | 119004.62
3080 | Crib Point Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  |  | 2025-10-10 | 2025-04-22 |  |  |  | 156095.13 | 156095.13
4217 | Dandenong West Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Bowdens | [6 empty] | 193851.92 | 193851.92 |  |  | PC Docs required 29/01 - No progress on paperwork, Tim to follow, still holding 10% payment
184 | Dromana Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd | [7 empty] | 315674.71 | 315674.71 |  |  | Awaiting VSBA to approve variations
1417 | Drouin West Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  |  |  | 2025-06-02 |  |  |  | 149400 | 149400
3215 | Eagle Point Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd | Insure Build |  |  | 2025-12-02 |  |  |  | 120658.63 | 120658.63
3790 | Edithvale Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots | [6 empty] | 558497.27 | 558497.27 |  |  | Variation 4 canopy demolition Ramp 2 21/01 - CFI not received? School funded works have been completed? 22//01 - All ramps completed. JMA still awaiting confirmation from RBS on CFI. School request concreted/pavement works, builder quoted ~$20k, school agreed and works completed by builder but formal PO was not provded to builder from the school. New principal not committing to funds despite email trail from previous principal. In dispute. 29/01 - No change
3942 | Elwood Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  |  |  | 2025-05-02 |  |  |  | 151438.08 | 151438.08
253 | Footscray Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  |  |  | 2025-06-30 |  |  |  | 165614.82 | 165614.82
8869 | Gleneagles Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa |  |  | 2025-12-12 |  |  |  | 159701.64 | 159701.64
5076 | Grovedale West Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  |  |  | 2025-08-06 |  |  |  | 319633 | 319633
1076 | Haddon Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  |  |  | 2025-10-20 |  |  |  | 68371.41 | 68371.41
4804 | Hamlyn Banks Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  |  |  | 2025-08-06 |  |  |  | 171711.34 | 171711.34
1098 | Hastings Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  |  |  | 2025-12-12 |  |  |  | 377241.37 | 377241.37
8904 | Hopetoun P-12 College | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd | Domain National |  |  | 2025-12-02 |  |  |  | 335680.08 | 335680.08
4697 | Horsham West and Haven Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd | Domain National |  |  | 2025-11-20 |  |  |  | 242119.37 | 242119.37
1147 | Inverleigh Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd | 0 |  |  | 2025-09-23 |  |  |  | 134470.67 | 134470.67
2776 | Inverloch Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  |  |  | 2025-07-21 |  |  |  | 103704.85 | 103704.85
1578 | Keilor Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  |  |  | 2025-07-17 |  |  |  | 83981.11 | 83981.11
7947 | Kensington Community High School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  |  |  | 2024-06-24 |  |  |  | 60000 | 60000
5135 | Kingsley Park Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | [6 empty] | 483842.02 | 483842.02 |  |  | Ramp K - internal ramp balustrade rectified Ramp E - tactiles Defects inspection to be scheduled CFI expected this week 29/01 - Matt (Principal) sent thru recent ESM non-compliant audit. Please check this
8716 | Kurnai College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  |  |  | 2024-07-10 |  |  |  | 0 | 0 |  |  | Removed from program ???
5256 | Kurunjang Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects | Hum | [6 empty] | 79158.44 | 79158.44 |  |  | Canopy Posts installed. Defects to be completed. Prior term 1 2026 29/01 - Anticipating School signoff end of this week (30/1) 12/02 - Principal not happy with stair nosing. HUM don't see any issue with the work at all. See photo email (Louise 12/2, nose caping). 26/02 - Going back tmr to secure screws
8910 | Lakeview Senior College | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects | 0 |  |  | 2024-07-04 |  |  |  | 0 | 0
5257 | Langwarrin Park Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | [6 empty] | 252186.87 | 252186.87 |  |  | Ramp A & C - photo of rectification required. Stormwater issue raised by the principal Ramp J - rails rectified and accepted Ramp F - Concreting works done.Handrails installed as per design and signed off by RBS. Ramp J - School request to modify handrail to pool access via footpath - H&L advised ramp will need to be fully demolished and reconstructed to accomdate the request Photo of tactiles required Expect CFI this week
3531 | Langwarrin Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | [6 empty] | 396409.09 | 396409.09 |  |  | Ramp C signed off by RBS. All ramps complete. Balustrade to Ramp L - school request still needs to be done. Will not affect CFI Tactiles to ramps - photo to be provided to RBS CFI expected this week
769 | Lara Lake Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  |  |  | 2025-10-06 |  |  |  | 253992.63 | 253992.63
5393 | Lardner and District Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  |  |  | 2025-09-08 |  |  |  | 193011.66 | 193011.66
1120 | Lindenow Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd |  |  |  | 2025-12-02 |  |  |  | 217599.43 | 217599.43
1231 | Lucknow Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd |  |  |  | 2025-12-02 |  |  |  | 60939.5 | 60939.5
5521 | Lyndhurst Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | [6 empty] | 178986.04 | 178986.04 |  |  | 19/01FHR has been relocated, tactiles installed and carpet tiles adjusted. Grab rail to be re-installed this week 29/01- All complete
7108 | Lyndhurst Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa |  |  | 2025-11-20 |  |  |  | 152161.62 | 152161.62
1604 | Malvern Central School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  |  |  | 2025-07-29 |  |  |  | 516264 | 516264
2586 | Malvern Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  |  |  | 2025-08-26 |  |  |  | 147237.6 | 147237.6
4669 | Malvern Valley Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd | Johnslyng | [6 empty] | 139022.13 | 139022.13 |  |  | CFI done, awaiting School signoff. Hand Rails and Retaining Wall defects to rectify the week of the 19th January prior term 1 2026 17/01 - Contractor conifrmed works complete as of 16/01 but School not happy with completed works. Defects inspection to be scheduled next week. All ramps accessible Dileep will not approve workflow until defects rectified Ross (Spaces) advised defect walkthru with Principal scheduled for 30/1
8015 | Maribyrnong Secondary College | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects | Pirotta | [6 empty] | 166040.65 | 166040.65 |  |  | 21/10 - Ramp 9 restumping works completed. Updated program to be provided. End of Feb target. Ramp works to commence next week. All other ramps - CFI this week 29/01 - Framing this week & concreting next week. Lightweigh cladding proposed. Moddex week after next. Still tracking to 27/2 5/02 - Concrete is poured, moddex may have some delay with fabrication (Pirotta to followup). Needs 2 weeks to install, it will arrive onsite on 20th Feb. 12/02 - Ramps schedule for next week (delivery 7am Mon), hopefully 27th finish. 26/02 - Weather delay, working Saturday and Monday for moddex & bitumen, final defect inspection Monday 2/03 (hopefully).
430 | Melton Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  |  |  | 2024-07-17 |  |  |  | 333538.8 | 333538.8
8030 | Mentone Girls Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots | [6 empty] | 728758.565 | 728758.565 |  |  | Ramp 6 - complete Ramp 4 - Feb 2026 - Re-design requiring approval - variation $ 20,672.83 for DS approval. $5k contribution by the school Intent for RBS to issue letter to allow use of completed ramps 29/01 - Still awaiting approval from VSBA, then need program from Builder.
4955 | Mentone Park Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots | [6 empty] | 351967.206 | 351967.206 |  |  | Small variation outstanding. 29/01 - Builder caused defect, needs rectification
1739 | Miners Rest Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects | Pirotta | [6 empty] | 299300.69 | 299300.69 |  |  | Expected CFI by 31/12/2025 with remedial works in January 2026 80m2 turf, handrail adjustments, backfill wall and clean up. 21/01 - Ramp 1 completed and compliant, All works expected to be completed this week. Ramp 5 kick rails to be installed 21/01. Final inspection this week Ramp 7 completed Defects inspection and final inspection to be scheduled. School request for a Yarning Circle to be discussed - committed by Pirotta RBS inspection 23/01/2016 (PDC attended) 29/01 - Kylie Principal on personal leave back in Feb (require her signoff) 12/02 - awaiting Kylie return and RBS return
8050 | Mirboo North Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  |  |  | 2025-08-29 |  |  |  | 232000 | 232000
2327 | Moorooduc Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  |  |  | 2025-04-22 |  |  |  | 42139.95 | 42139.95
4117 | Moriac Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  |  |  | 2025-08-06 |  |  |  | 56567.8 | 56567.8
5568 | Morwell Central Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  |  |  | 2025-08-21 |  |  |  | 65530.8 | 65530.8
4975 | Morwell Park Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  |  |  | 2025-08-21 |  |  |  | 149236.75 | 149236.75
5205 | Mossgiel Park Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | [6 empty] | 105367.33 | 105367.33 |  |  | failed final inspection, rectification eta? Clearance between handrail to be added to Performance Solution.
427 | Mount Clear Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  |  |  | 2025-07-29 |  |  |  | 113217.77 | 113217.77
8102 | Mount Eliza Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  |  |  | 2025-08-28 |  |  |  | 394738.81 | 394738.81
2248 | Nar Nar Goon Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 19 | JMA Architects |  |  |  | 2024-07-10 |  |  |  | 2000 | 2000
2103 | Newington Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  |  |  | 2025-04-29 |  |  |  | 128938.31 | 128938.31
5410 | Niddrie Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  |  |  | 2024-07-18 |  |  |  | 1587.5 | 1587.5
8865 | Nossal High School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Hum | [6 empty] | 109059.3 | 109059.3 |  |  | Planter box lid variation and defect works to complete. 22/01 - Lid variation approved by Dileep/VSBA. Awaiting CFI with Hum. Defect inspections to be conducted thereafter 29/01 - Awaiting HUM program. 3/02 - Received Email from school (via Tim M) advising of final re-keying costs (~$13k). 05/02 - End of next week forecast completion 10/02 - Email received from school, Contractor illegal entry into school on Saturday (cut padlock), filled planter box & didn't address defects. 26/02 - Asphalt outstanding, school was thinking pit lid was also being done.
4780 | Overport Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | [6 empty] | 139855.98 | 139855.98 |  |  | Completed June. Bella to advise why PCC not yet issued - URGENT. Defects inspection not done
5504 | Pakenham Lakeside Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 19 | JMA Architects |  |  |  | 2025-08-22 |  |  |  | 127939.01 | 127939.01
4843 | Parktone Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 18 | JMA Architects |  |  |  | 2025-10-08 |  |  |  | 263495.13 | 263495.13
5480 | Parkwood Green Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  |  |  | 2025-09-15 |  |  |  | 202249.64 | 202249.64
8725 | Patterson River Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | [6 empty] | 255207.7 | 255207.7 |  |  | Work scope complete
5369 | Pentland Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  |  |  | 2025-11-24 |  |  |  | 439502.5 | 439502.5
8847 | Point Cook Senior Secondary College | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  |  |  | 2024-06-17 |  |  |  | 2000 | 2000
1194 | Portland North Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  |  |  | 2025-09-18 |  |  |  | 178367.29 | 178367.29
489 | Portland Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  |  |  | 2025-09-18 |  |  |  | 83407.83 | 83407.83
4663 | Roslyn Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  |  |  | 2025-08-06 |  |  |  | 69509.5 | 69509.5
267 | Sandringham Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge |  |  |  | 2024-07-23 |  |  |  | 54636.74 | 54636.74 |  |  | Removed from scope
8875 | Somerville Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  |  |  | 2025-08-18 |  |  |  | 88711.6 | 88711.6
1090 | Sorrento Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  |  |  | 2025-07-31 |  |  |  | 93682.9 | 93682.9
8911 | Springside Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  |  |  | 2025-03-20 |  |  |  | 95765.17 | 95765.17
4741 | St Albans East Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  |  |  | 2025-06-30 |  |  |  | 82.0256 | 82.0256
1646 | St Arnaud Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd | Domain National | [6 empty] | 273386.45 | 273386.45 |  |  | Hazardous Materials. December Holidays works commence 6th January 2026. program pending from Domain.
8854 | Tarneit Senior College | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  |  |  | 2025-07-29 |  |  |  | 213191.37 | 213191.37
2065 | Teesdale Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  |  |  | 2025-09-25 |  |  |  | 148082.94 | 148082.94
5479 | Timbarra P-9 College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Hum | [6 empty] | 198029.71 | 198029.71 |  |  | Ramp 15 TBC Expected PC 27/02/2026 (program to be submitted by Hum) 29/01 - Demo occurred today, pouring next week. Still tracking mid Feb 05/02 - R15 concrete pour done, handrails next week, 12/02 forecast completion 26/02 - Awaiting program to closeout. Small demo, removal handrails, removal concrete, pour and set, re-inspect. Hoping to finish by 7/03.
5414 | Toolern Vale and District Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  |  |  | 2025-07-31 |  |  |  | 123787.16 | 123787.16
3016 | Toorak Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  |  |  | 2025-10-06 |  |  |  | 191343.26 | 191343.26
3968 | Toorloo Arm Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd |  |  |  | 2025-12-02 |  |  |  | 78026.63 | 78026.63
4700 | Traralgon (Liddiard Road) Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd | Jointly |  |  | 2025-11-07 |  |  |  | 322258.75 | 322258.75
8803 | Traralgon College (Ramps) | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd | Jointly | [6 empty] | 2178875.51 | 2178875.51 |  |  | waiting on school sign-off
8804 | Traralgon College (RFE) | SEV | 2023-24_FYQ2_CYQ4_W40-53 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd | Jointly | [6 empty] | 2178876.51 | 2178876.51 |  |  | Ramp work complete. RFE Roof December Holidays, The steel installation will occur between 5th and 23rd Jan 2026 exclusion zone required. Structural steel works are scheduled to occur between 8th January and 15th January 14/01 - PCC walkthru 9 Feb with School. CFI next week (hopefully) 21/01 - completion 6 Feb. Defects inspection 8 Feb 28/01 - New forecast 9 Feb. 04/02 - Still tracking. Awaiting Dileep approval for absestos removal (Jul 2025) 12/02 - Roof works completed yesterday
5553 | Tulliallan Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects |  |  |  | 2025-10-20 |  |  |  | 168439.97 | 168439.97
8405 | University High School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  |  |  | 2025-06-30 |  |  |  | 45497.19 | 45497.19
8827 | Warragul Regional College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  |  |  | 2025-11-10 |  |  |  | 547164.82 | 547164.82
1813 | Wendouree Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects | Pirotta | [6 empty] | 150509.35 | 150509.35 |  |  | Ramps 2 and 1 Final inspection this week 21/01 - All works completedand currently safe to occupy. Ramp 3 CFI received 29/01 - Defects complete yesterday 28/01
649 | Werribee Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects | Pirotta | [6 empty] | 253536.46 | 253536.46 |  |  | CFI received 18/12/2025 21/01 - defects rectification to be completed this week. cyclone fence scheduled 22/10 - Pirotta to provide temp fencing if cyclone fence not reworked. Fake turf between water tank lsab and new paving gap. FInal defects inspection by Friday.
8470 | Westall Secondary College | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots | [6 empty] | 763521.8 | 763521.8 |  |  | Ramp 14 - non-DDA ramp, school request ramp over step to be treated as school defect. Will seek CFI with RBS to be issued next week
8475 | Williamstown High School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  |  |  | 2025-08-06 |  |  |  | 503693.85 | 503693.85
5319 | Woodlands Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | [6 empty] | 159965.71 | 159965.71 |  |  | CFI expected this week
5549 | Wyndham Vale Primary School | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  |  |  | 2025-07-29 |  |  |  | 58188.94 | 58188.94
4807 | Yarraman Oaks Primary School | SEV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Bowdens | [6 empty] | 97358.45 | 97358.45 |  |  | Covered way roof works completd. Defects inspection to be scheduled next week 26/02 - Asphalt work done yesterday.
5520 | Yuille Park P-8 Community College | SWV | 2023-24_FYQ2_CYQ4_W40-52 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  |  |  | 2025-07-29 |  |  |  | 24573.6 | 24573.6
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Auto generated, 6months from Construction Complete
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Auto generated, 3months from DLP Complete
Note on Q70: Aaron Rice: Extra Ramp access approved for addition.
Note on R70: Aaron Rice: Extra Ramp access approved for addition.
Note on Q106: Aaron Rice: RAMPS and RFE works to be included. Approx total estimated values total $1.7m
Note on R106: Aaron Rice: RAMPS and RFE works to be included. Approx total estimated values total $1.7m

## Status
| Total Schools | 111 | [5 empty] | Count | 83 |  |  |  | 63 | 1
[8 empty] | Progress | 74.77% |  |  |  | 56.76% | 0.9009%
| School Name | School No | Region Name | Final PNN | Bundle ID | PDC | Contractor | Last Milestone Achieved | Construction Complete (Forecast / Actual) | Defects Closed | CFI Achieved | School Signoff | Practical Completion (Workflow Closed) | Final Completion / DLP | Comments | Sky 50 | sent by 27/02 | Sent by (week 13/2) | Sent by 06/02 | Sent by 30 / 01 comments | Sent by 30/01 | Sent by 23/01 | Sent by 16/01 | Sent by 9/01 | Sent by 19/12 | Comments 16 / 01 | Priority ? | to | cc
| Albert Park College | 8889 | SEV | 8889_07 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  | Construction Complete | Complete 14/06/2024 | [10 empty] | Closed for Comms | NA
| Alberton Primary School | 1 | SEV | 0001_05 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  | Construction Complete | Complete 26/06/2024 | [10 empty] | Closed for Comms | NA
| Alkira Secondary College | 8874 | SEV | 8874_04 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | Construction Complete | Complete 11/12/2025 | NA | 2025-12-11 | 19/01/2026 |  |  | Works completed with CFI issued 11/12/2025 with documentation, sign off and handover expected Janaury 2026. | Yes |  |  |  | works completed as per john spronget email. sign off and site walk to be arranged. AG (wrong school. Signoff received awaiting workflow closeout. No comms to school) | Andrew - Final | Joey | Andrew | Andrew | Aaron |  |  | john.shaw@education.vic.gov.au, Dale.Robb@education.vic.gov.au, bernard.gibney2@education.vic.gov.au | eileen.box@education.vic.gov.au
| Altona Green Primary School | 5287 | SWV | 5287_06 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects | Hum | Construction Complete | 2026-02-02 | no | 2026-01-28 |  |  |  | Hum 1:1 Defects with handrails require 1000mm width. January 2027 Final sign off by RBS required - modifications to the handrail required. LIkely next week Ramps accessible before start of school term 29/01 - CFI achieved, school signoff to be scheduled with PDC (targeting Mon 2 Feb) 05/02 - Outstanding defects. HUM to close workflow 12/02 - Outstanding defects, no progress. 26/02 - Defect rectification on site from tmr | Yes |  |  |  | PDC visiting next week to review works and seek school sign off. | Andrew - Final | Joey | Andrew | Andrew | Aaron | Hum going out onsite to measure actuals/clearances and work with PDC. |  | David.King@education.vic.gov.au
| Altona North Primary School | 4931 | SWV | 4931_06 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects | Hum |  | 2026-03-15 |  | 2025-07-12 |  |  |  | Hum 1:1 Inspection failed due to changer of foundation by Hum. January 2027 Ramp 3 - planter box to be provided Ramp 2 - Gate issues. measurement provided to manufacturer. LIkely won't be an issue with the CFI Ramps in use 29/01 - Louise said all outstanding issues have a way forward (handrail clearance been re-measured, break in handrail on inner bend, purchase of planter boxes (school acceptance to be sought prior to purchse, cyclone gate installation and design with lower level clarified. Gate install end Feb, other mods done prior. HUM to provide program. 5/02 - Waiting for shop drawings from supplier, wants to get that approved by school first. Handrails next week. Ashphalt rectification after the fence. 12/02 - No progress Ramp 2, still waiting on shop drawing. Little defects remaining, nothing done yet. 26/02 - Moddex visiting tmr, Awaiting confirmation of dates for gate install (tmr) | Yes |  |  |  | Hum have advised they are looking to close out the minor defects next week. however the fencing and gate will need to be ordered and may have a lead time of 2-4 weeks just for the gate. Additionally, the planter boxes will need to be costed by Hum so we can provide those as per the concersation and request with the school. | Andrew |  | Andrew | Andrew | Aaron | Ramp 2 gate handrail 1m clearance, school wants planter boxes to reduce glare from new ramp, sharp kickrail edges, Cyclone gate design with lower level ambiguous. Hum going out onsite to measure actuals/clearances and work with PDC. | Problem - 60th Anniversary, etc | Lee.Blunt@education.vic.gov.au; Robyn.Gregson@education.vic.gov.au
| Ararat Primary School | 800 | SWV | 0800_06 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  | Practical Completion | Complete 20/10/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Ardeer Primary School | 4848 | SWV | 4848_06 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  | Construction Complete | Complete 4/06/2024 | [10 empty] | Closed for Comms | NA
| Bacchus Marsh College | 8777 | SWV | 8777_09 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  | Practical Completion | Complete 29/10/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
* | Bairnsdale Secondary College | 8466 | SEV | 8466_13 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd | Pattersons | Construction Complete |  | No | Yes |  |  |  | RBS final inspection identified defects at Ramps 3, 5, 16 and 20. Ramp 5 & 16 to be rectified 28/01 - Inspection done but BS won't issue CFI - waiting on payment for additional inspections (in discussion with Pattersons & Spaces). Defects still remain (no ETA yet) 4/02 - No change. Pattersons won't pay BS. 10% construction value is still being held by PDC. (About 5 or 6 additional inspections done, BS wants to be paid for this). 4/03 - Still awaiting Pattersons to advise of delivery (from Alex) to fix defects. Andy and Dileep attended this site (see email) | Yes |  | PDC - Ross |  | Spaces are seeking to attend site to review the defects and school walk through. 4/02/2026 | Andrew | Joey | Andrew | Andrew | Aaron |  | Problem school | clare.stone@education.vic.gov.au |  | ross@spaces.com.au; micah@spaces.com.au
| Barton Primary School | 5560 | SEV | 5560_03 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | Practical Completion | Complete 12/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA
| Beaumaris North Primary School | 4803 | SEV | 4803_08 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | Construction Complete |  | no |  |  | 2026-06-02 |  | CFI Paperwork expect Tues/Wed 21 Jan. RBS has now been paid Defects inspection to be scheduled next week GRN demob from site | Yes |  |  | H&L | Works are completed and building surveyor has inspected with the CFI's expected iminently. H&L Architects and GRN Builder will contact the school to arrange a site walk and ensure defects are completed. School sign off will be sought and 6 months DLP will apply to the works. |  | Joey | Andrew | Andrew | Andrew |  |  | Lee.Skaftouros@education.vic.gov.au; Nicola.Hajncl@education.vic.gov.au; angus.ross@education.vic.gov.au
| Bellbrae Primary School | 319 | SWV | 0319_10 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  | Construction Complete | Complete 9/07/2025 | [10 empty] | Closed for Comms | NA
| Berwick Secondary College | 7603 | SEV | 7603_08 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Hum |  | 2026-02-09 | No |  |  |  |  | Agreed to get out RBS for CFI of all completed ramps asap to reduce distruption to school, ramp R4 & likely R1 won't be done in time. Recently new Principal & FM. Ramp 1: Completion 04.02.26 • Landing poured yesterday • Rubber ramp to be measured today (23.01.26) lead time 5-7 days manufacture. 4 Feb forecast • Install of temp ramp & handrail, completed 29.01.2026 to allow access. Final Ramp 4: ON HOLD. awaiting engineers' advice 29/01. Balustrade been replaced but now all ramp is flexing & could be unsafe, struc engineer to inspect 23/01. Handrails to be removed Ramp 7: Completion 29.01.2026 • Asphalts poured, Bollard footings poured, Install of bollards & line marking - Wednesday 28.01.2026 (now 2nd Feb) Ramp 9: Completion 09.02.26 Carpentry to be book in conjunction with ramps 1 & 7 as it's a day visit. Ramp 10: Completion 09.02.26 Carpentry to be book in conjunction with ramps 1 & 7 as it's a day visit. Final Inspection on 10 Feb. 5/02 - Works finished except R4 end next week 13/02 26/02 - Carpentry done R1,4,7,10. R4 handrails removed and made good, R1 rubber done. R9 new issues. R10 Done. Awaiting updated modex shop drawings. Maybe mid 15/03. | Yes |  |  |  | Ramp 1 was attended to this week to ensure accessible to staff and student until the final hand rails and rubber ramp can be installed circa 4th February due to lead times. Ramp 4 has been assessed by the engineer. Ramp 7, 9 and 10 are scheuled to complete by HUM 2nd-9th February when all works should be completed. |  | Joey | Andrew | Andrew | Aaron | Ramp 4 balustrade removed, replaced, but ramp flexing & unsafe. Change of principal & FM. | Sky very interested | Millard@education.vic.gov.au; John.Inglis@education.vic.gov.au
| Buckley Park College | 7670 | SWV | 7670_04 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects | Pirotta |  | 2026-02-06 | [5 empty] | Pirotta 1:1 Ramp 17 remaining handrails by Moddex by 23/01/2026 21/01 - Ramp 17 frame to be installed this week. Decking and cladding next week and nosing/handrails the following week. target completion 30 Jan. Final Inspection Jan 30 29/01 - Slipped by one week Ramp 17 (hot weather), ramp to complete this week, nosing next week. 5/02 - Cleanup next week, signoff next week. 26/02 - Seeking signoff on Mon 2/03 | Yes |  |  |  | Ramp 17 construction was due for completion 30/01/2026, extreme heat mayhave caused some delay, with the tactiles to be added 6th February as advised by Pirotta and followed by a site inspection, review and sign off. | Andrew | Cameron | Andrew | Andrew | Aaron | New school Principal |  | tegan.knuckey@education.vic.gov.au, harold.cheung@education.vic.gov.au
| Canadian Lead Primary School | 5383 | SWV | 5383_05 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects | Pirotta |  | 2026-03-20 |  | 2026-03-27 |  |  |  | Pirotta 1:1 Ramp 3 23/01/2026 and Ramps 1 and 2 by 27th February 2026. 21/01 - Ramp 3 will commence 27-Janby Moddex. Ramp 1 & 2 fabrication on-going. Potential delay for Ramp 1 29/01 - Ramp 3 starting today (hot weather delay). R1&2 shop design awaiting from Moddex, maybe Building Permit amendment. Forecast date 27/2 is likely at risk with R1&2. 5/02 - Cameron/David/Grymbos plan to submit BP amendment this week. Anticipate 2 weeks for approval, then commence onsite (say 1 after). In parallel moddex manufacture. Say 2 weeks construct, 1 week moddex & clean up (eta 20/03 for complete), CFI signoff probably week after. 12/02 - Ramp 3 frame approved, next week concrete, nosing & temp fence. R1&2 still in shop drawings, manufacturing yet to start, building permit mod required. 26/02 - R3 delayed (probably 1week work). R1&2 Amended BP not achieved, need update from Pirotta, last PC date 20/3 very unlikely. | Yes |  |  |  | As advised from Pirotta, Ramp 3 moddex intallation of handrails between 29/01/2026 to 13/02/2026. Ramp 1 and Ramp 2 are both pending final design with Moddex. forecast due date for completion of all ramps is 27/02/2026. | Andrew | Cameron | Andrew | Andrew |  | Ramp 3 changed to commence 27/1 & expected for about 2wks |  | Clete.Smith@education.vic.gov.au; Christina.Drummond@education.vic.gov.au
| Carnegie Primary School | 2897 | SEV | 2897_09 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  | Practical Completion | Complete 12/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Carwatha College P-12 | 5435 | SEV | 5435_08 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Bowdens |  | 2026-03-01 |  | 2026-03-06 |  | 2026-03-13 |  | 27/01: Ramp 12 to be maintained. non-DDA accessible ramp sign, removable bollards and map showing alternate DDA access route to be installed. Transfer cost to Ramp 18 - school :endorsed 29/01 - Principal sent recent email, please review. Letter of Completion received from RBS (to Tim Meldrum). Need school endorsement of re-design of Ramp 18 (school entrance access). 5/02 - Currently doing 17 forecasting completion 9/2, Ramp 18 still needs approval from VSBA (Dileep awaiting final costs (action with JMA). Carpark disruption required for R18 construction, builder wants help/support from school. R24 needs approval (coupled with ramp 18 proximity), will be constructed together. 26/02 - Costings need reviews, much much higher than previous ramps done. | Yes |  |  |  | Tim from JMA to respond to Patrick Mulcahy once Bowdens confirm. Patrick has signed off on the Ramp 18 design. Bowdens to finalise quote for approval. Works can commence as per a revised program to be provided by Bowdens. Canopy/posts works and Ramp 17 to progress next week. Engineer has advised the existing concrete footings are suitable for the new posts to replace the rotted ones. |  | Joey | Andrew | Andrew | Aaron | Final design package to go to Dileep for final costing. New construction manager Quentin Greystone | Problem site | patrick.mulcahy@education.vic.gov.au, john.webb3@education.vic.gov.au |  | patrick@bowdencorp.com.au, duncan.lindsay@bowdencorp.com.au, yogev.keren@bowdencorp.com.au
| Chelsea Heights Primary School | 3341 | SEV | 3341_09 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots | Practical Completion |  |  | Issued |  | 2026-01-15 |  | DLP Period | Yes |  |  |  | Closed for Comms | NA | N/R | Andrew | Andrew | Andrew | PC Complete this week |  | steven.capp@education.vic.gov.au
| Chilwell Primary School | 2061 | SWV | 2061_08 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  | Practical Completion | Complete 6/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Clayton South Primary School | 4384 | SEV | 4384_06 | PMP_OPO_Nov'23Bundle 18 | JMA Architects |  | Construction Complete | Complete 9/07/2024 | [10 empty] | Closed for Comms | NA
| Clyde Primary School | 3664 | SEV | 3664_08 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | Practical Completion | Complete 12/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA |  |  |  | Aaron
| Coburn Primary School | 5090 | SWV | 5090_04 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects | Hum |  | 2026-02-20 |  | 2026-02-18 |  |  |  | Hum 1:1 Ramp 12 5/01/2026 but likely February PCC. R10 CFI received R12 - demo complete 29/01 - demo delayed (done yesterday). Concrete pour for today. Forecasting all done 20/2 2/02 - Louise advised of permit issue causing delay to concrete and carpentry. awaiting update 5/02 - Concrete pour forecast 14/02, hopefully all complete this same week. School unhappy with work during term - want weekday only. 12/02 - 27th forecast completion. Demo and concrete works not to happy during the week 26/02 - Demo complete, concrete pour tmr. 11/03 forecast completion, proposing walkthru on same day with school | Yes |  |  |  | Only Ramp 12 works remaining, concrete pour was scheduled 29/01, handrails expected 16/02 and final inspection expected 20th Feb 2026. | Andrew | Joey | Andrew | Andrew | Aaron | CFI Tues next week (R9) R12 (demo this week, next week new ramp, complete 11 Feb). School notified of date "happy". David requested shop drawings from Moddex to review |  | Cindy.Neilson@education.vic.gov.au
| Colac Secondary College | 8864 | SWV | 8864_05 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  | Construction Complete | Complete 15/07/2025 | [10 empty] | Closed for Comms | NA
| Cranbourne Carlisle Primary School | 5510 | SEV | 5510_03 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | Practical Completion | Complete 18/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA |  |  |  | Aaron
| Cranbourne East Primary School | 5518 | SEV | 5518_03 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | Practical Completion | Complete 12/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA |  |  |  | Aaron
| Crib Point Primary School | 3080 | SEV | 3080_05 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  | Practical Completion | Complete 22/04/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Dandenong West Primary School | 4217 | SEV | 4217_07 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Bowdens | Construction Complete | 2026-09-12 |  | 2026-01-14 |  | 2026-01-23 |  | PC Docs required 29/01 - No progress on paperwork, Tim to follow, still holding 10% payment | Yes |  |  |  | JMA Architects to seek handover and completion documentation from Bowdens. |  | N/R |  | Andrew | Aaron | Doc to close now |  | Joshua.Bourke@education.vic.gov.au
| Dromana Primary School | 184 | SEV | 0184_08 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  | Practical Completion | Complete 22/12/2025 | yes | yes | yes | yes |  | Awaiting VSBA to approve variations | Yes |  |  |  | Closed for Comms | NA
| Drouin West Primary School | 1417 | SEV | 1417_08 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  | Practical Completion | Complete 2/06/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Eagle Point Primary School | 3215 | SEV | 3215_07 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd | Insure Build | Practical Completion | Complete 2/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA | [5 empty] | Problem school
| Edithvale Primary School | 3790 | SEV | 3790_05 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots | Construction Complete | 2025-12-19 | 30/01/2026 | 2026-01-23 |  | 2026-01-30 |  | Variation 4 canopy demolition Ramp 2 21/01 - CFI not received? School funded works have been completed? 22//01 - All ramps completed. JMA still awaiting confirmation from RBS on CFI. School request concreted/pavement works, builder quoted ~$20k, school agreed and works completed by builder but formal PO was not provded to builder from the school. New principal not committing to funds despite email trail from previous principal. In dispute. 29/01 - No change | Yes |  |  |  | Ramp 2 Canopy demo was completed. JMA Architects following up on additional school request for additional concrete to remove the uneven areas in the travel space. Please follwo up with Tim Meldrum JMA. |  | N/R |  | Andrew | Andrew |  | Haley (previous principal) has left | steven.capp@education.vic.gov.au
| Elwood Primary School | 3942 | SEV | 3942_06 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  | Practical Completion | Complete 2/05/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Footscray Primary School | 253 | SWV | 0253_06 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  | Practical Completion | Complete 30/06/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Gleneagles Secondary College | 8869 | SEV | 8869_06 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | Practical Completion | Complete 12/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA |  |  |  | Aaron
| Grovedale West Primary School | 5076 | SWV | 5076_07 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  | Practical Completion | Complete 6/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Haddon Primary School | 1076 | SWV | 1076_07 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  | Practical Completion | Complete 20/10/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Hamlyn Banks Primary School | 4804 | SWV | 4804_11 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  | Practical Completion | Complete 6/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Hastings Primary School | 1098 | SEV | 1098_07 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  | Practical Completion | Complete 12/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA
| Hopetoun P-12 College | 8904 | SWV | 8904_15 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd | Domain National | Practical Completion | Complete 2/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA |  |  |  | Andrew
| Horsham West and Haven Primary School | 4697 | SWV | 4697_09 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd | Domain National | Practical Completion | Complete 20/11/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA
| Inverleigh Primary School | 1147 | SWV | 1147_06 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  | Practical Completion | Complete 23/09/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Inverloch Primary School | 2776 | SEV | 2776_05 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  | Practical Completion | Complete 21/07/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Keilor Primary School | 1578 | SWV | 1578_04 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  | Practical Completion | Complete 17/07/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Kensington Community High School | 7947 | SWV | 7947_05 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  | Practical Completion | Complete 24/06/2024 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Kingsley Park Primary School | 5135 | SEV | 5135_06 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | Construction Complete |  | Yes |  |  | 2026-06-02 |  | Ramp K - internal ramp balustrade rectified Ramp E - tactiles Defects inspection to be scheduled CFI expected this week 29/01 - Matt (Principal) sent thru recent ESM non-compliant audit. Please check this | Yes |  |  | H&L | Works are completed and building surveyor has inspected with the CFI's expected iminently. H&L Architects and GRN Builder will contact the school to arrange a site walk and ensure defects are completed. School sign off will be sought and 6 months DLP will apply to the works. The ESM issue has been reviewed and the height appears compliant due to the levels being less than 1m fall risk and complies to the NCC. CFI to be provided to close out same. |  | Joey | Andrew | Andrew | Andrew |  |  | gill.gray@education.vic.gov.au; Matthew.Brand@education.vic.gov.au
| Kurnai College | 8716 | SEV | 8716_13 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  | Construction Complete | Complete 10/07/2024 | [5 empty] | Removed from program ??? |  |  |  |  | Closed for Comms | NA
| Kurunjang Primary School | 5256 | SWV | 5256_08 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects | Hum | Construction Complete | 2026-01-30 | yes 30/01/2026 |  |  |  |  | Canopy Posts installed. Defects to be completed. Prior term 1 2026 29/01 - Anticipating School signoff end of this week (30/1) 12/02 - Principal not happy with stair nosing. HUM don't see any issue with the work at all. See photo email (Louise 12/2, nose caping). 26/02 - Going back tmr to secure screws | Yes |  |  |  | Defects completed, we were advised the school is happy the defects have been attended to. 1:1 architects and HUM to seek school sign off acklowledgement. There is a six month DLP if any future defects arise in this time. | Andrew - Final | N/R | Andrew | Andrew | Aaron | Landscape slipping issues complete. Nosing for stairs outstanding (20 Jan for install). PCC end of month (School to signoff) Expect CFI this week | Wants updates | thomas.goddard@education.vic.gov.au
| Lakeview Senior College | 8910 | SWV | 8910_05 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  | Construction Complete | Complete 4/07/2024 | [10 empty] | Closed for Comms | NA
| Langwarrin Park Primary School | 5257 | SEV | 5257_07 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | Construction Complete | check 19/12/2025 | no | RBS inspection scheduled 21/01 |  | 2026-06-02 |  | Ramp A & C - photo of rectification required. Stormwater issue raised by the principal Ramp J - rails rectified and accepted Ramp F - Concreting works done.Handrails installed as per design and signed off by RBS. Ramp J - School request to modify handrail to pool access via footpath - H&L advised ramp will need to be fully demolished and reconstructed to accomdate the request Photo of tactiles required Expect CFI this week | Yes |  |  | H&L | Works are completed and building surveyor has inspected with the CFI's expected iminently. H&L Architects and GRN Builder will contact the school to arrange a site walk and ensure defects are completed. School sign off will be sought and 6 months DLP will apply to the works. The Architect will review the Ramp J and work through the school concerns and any additonal scope would need to be reviewed and approved by VSBA to be able to proceed. The ESM items will be assessed by the architect and confirmed with the building surveyor. Architect to coordinate with the school. |  | JOey | requested GRN | Andrew | Andrew | close | Problem site | David.Geddes@education.vic.gov.au; debraanne.haddow@education.vic.gov.au
| Langwarrin Primary School | 3531 | SEV | 3531_04 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | Construction Complete | 2026-02-02 | no |  |  | 2026-06-02 |  | Ramp C signed off by RBS. All ramps complete. Balustrade to Ramp L - school request still needs to be done. Will not affect CFI Tactiles to ramps - photo to be provided to RBS CFI expected this week | Yes |  |  | H&L | With the installation of the balustrade this week, works are completed and building surveyor has inspected with the CFI's expected iminently. H&L Architects and GRN Builder will contact the school to arrange a site walk and ensure defects are completed. School sign off will be sought and 6 months DLP will apply to the works. |  | Joey | requested GRN | Andrew | Andrew |  | Problem site | Monique.Corcoran@education.vic.gov.au; nicola.pepper@education.vic.gov.au; Rowan.Balzary@education.vic.gov.au; Angela.Stacey@education.vic.gov.au
| Lara Lake Primary School | 769 | SWV | 0769_09 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  | Practical Completion | Complete 6/10/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Lardner and District Primary School | 5393 | SEV | 5393_05 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  | Practical Completion | Complete 8/09/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Lindenow Primary School | 1120 | SEV | 1120_07 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd |  | Practical Completion | Complete 2/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA |  |  |  | Aaron
| Lucknow Primary School | 1231 | SEV | 1231_05 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd |  | Practical Completion | Complete 2/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA |  |  |  | Aaron
| Lyndhurst Primary School | 5521 | SEV | 5521_03 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | Construction Complete | Complete 29/01/2026 | Yes |  |  |  |  | 19/01FHR has been relocated, tactiles installed and carpet tiles adjusted. Grab rail to be re-installed this week 29/01- All complete | Yes |  |  |  | All works scope has been completed as advised by Chippa Constructions. 1:! Architects to review for defects with the school and seek sign off acknowledgment. A six month DLP applies to works for any defect items that may occur in that period. | Andrew - Final |  |  | Andrew | Aaron |  | Problem site | Monique.Corcoran@education.vic.gov.au
| Lyndhurst Secondary College | 7108 | SEV | 7108_06 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | Practical Completion | Complete 20/11/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA
| Malvern Central School | 1604 | SEV | 1604_05 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  | Practical Completion | Complete 29/07/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Malvern Primary School | 2586 | SEV | 2586_06 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  | Practical Completion | Complete 26/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Malvern Valley Primary School | 4669 | SEV | 4669_06 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd | Johnslyng | Practical Completion | Complete | No | yes | yes | no | yes 14/06/2026 | CFI done, awaiting School signoff. Hand Rails and Retaining Wall defects to rectify the week of the 19th January prior term 1 2026 17/01 - Contractor conifrmed works complete as of 16/01 but School not happy with completed works. Defects inspection to be scheduled next week. All ramps accessible Dileep will not approve workflow until defects rectified Ross (Spaces) advised defect walkthru with Principal scheduled for 30/1 | Yes |  |  |  | Spaces architects attended the school 30/01/2026 and have advised that the school’s concerns with Ramp 1 have now been addressed by the contractor to the school’s satisfaction. It was noted the new defect (the small section of kerb railing at Ramp 3 which has snapped off) will be rectified by JLG by Friday 6th February. Please let us know if this does not occur. | Andrew - Final | Joey | Andrew | Andrew |  |  | Problem site | amy.tinetti@education.vic.gov.au | Brendyn Flood <brendynflood@gmail.com>; Zaim Zeneli <Zaim.Zeneli@education.vic.gov.au>
| Maribyrnong Secondary College | 8015 | SWV | 8015_09 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects | Pirotta |  | 2026-02-27 | [5 empty] | 21/10 - Ramp 9 restumping works completed. Updated program to be provided. End of Feb target. Ramp works to commence next week. All other ramps - CFI this week 29/01 - Framing this week & concreting next week. Lightweigh cladding proposed. Moddex week after next. Still tracking to 27/2 5/02 - Concrete is poured, moddex may have some delay with fabrication (Pirotta to followup). Needs 2 weeks to install, it will arrive onsite on 20th Feb. 12/02 - Ramps schedule for next week (delivery 7am Mon), hopefully 27th finish. 26/02 - Weather delay, working Saturday and Monday for moddex & bitumen, final defect inspection Monday 2/03 (hopefully). | Yes |  | Pirotta - Guliano 12/2 |  | All Ramps except Ramp 9 are completed and accessible by the school. Ramp 9 progressing woith boxing and steel by 30/01 with concrete pour expected 3/02 and moddex steel to be completed by 27/02/2026 at the latest. | Andrew | Cameron | Andrew | Andrew | Aaron | Ramp 9 restumping end next week, excav/geotech done. Expect end Feb. CFI expected 14/01 for all other ramps and then for the final | Michael being vocal | Michael.Keenan@education.vic.gov.au
| Melton Primary School | 430 | SWV | 0430_06 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  | Construction Complete | Complete 17/07/2024 | [10 empty] | Closed for Comms | NA
| Mentone Girls Secondary College | 8030 | SEV | 8030_07 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots |  | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | Ramp 6 - complete Ramp 4 - Feb 2026 - Re-design requiring approval - variation $ 20,672.83 for DS approval. $5k contribution by the school Intent for RBS to issue letter to allow use of completed ramps 29/01 - Still awaiting approval from VSBA, then need program from Builder. | Yes |  |  |  | All Ramps other than Ramp 4 are completed. JMA Architects following up on additional school request for additional concrete to remove the uneven areas in the travel space. Please follow up with Tim Meldrum JMA. |  | Joey |  | Andrew | Andrew | Roof works to Ramp see forecast for end next week (23/1). CFI for all completed ramps. Ramp for large effort |  | Leigh.Roberts@education.vic.gov.au
| Mentone Park Primary School | 4955 | SEV | 4955_08 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots | Construction Complete | 2025-12-19 | No | 2025-10-10 | yes |  |  | Small variation outstanding. 29/01 - Builder caused defect, needs rectification | Yes |  |  |  | All works completed, builder has been requested to rectify defect drain strip. Please follow up with TIm Meldrum if this is yet to occur. |  | Joey |  | Andrew | Andrew | Variation/Defect to submit to Dileep ($1k) |  | leisa.higgins@education.vic.gov.au'
| Miners Rest Primary School | 1739 | SWV | 1739_07 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects | Pirotta | Practical Completion | 2026-02-02 | 23/01/2026 inspection |  |  | 2026-02-27 |  | Expected CFI by 31/12/2025 with remedial works in January 2026 80m2 turf, handrail adjustments, backfill wall and clean up. 21/01 - Ramp 1 completed and compliant, All works expected to be completed this week. Ramp 5 kick rails to be installed 21/01. Final inspection this week Ramp 7 completed Defects inspection and final inspection to be scheduled. School request for a Yarning Circle to be discussed - committed by Pirotta RBS inspection 23/01/2016 (PDC attended) 29/01 - Kylie Principal on personal leave back in Feb (require her signoff) 12/02 - awaiting Kylie return and RBS return | Yes |  |  |  | All works completed, builder has been requested to rectify Ramp 5. All ramps are open and CFI has been received. 1:1 Architects and Pirotta to seek school sign off and endorsement, noting that there is a six month defect liabilty period to cover any issues that may arise in this time. We appreciate that the Principal is away until the 29th February 2026 but we cannot delay closing out these works. The school acklowledgement is only to say the scope of works as agree has been completed. Any concerns or comments can be noted on the sign off form as a record. Happy to discuss. | Andrew | Cameron | Andrew | Andrew | Aaron | CFI 13/1 - Ramp7 failed (reduced width, could be pedantic, 1:1 to follow). Ramp 5 at 90% to complete this week (tactiles & handrail). Rebooking inspection for next Wed 21/1. PCC 27/02/26 |  | kylie.nissen@education.vic.gov.au
| Mirboo North Secondary College | 8050 | SEV | 8050_06 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  | Practical Completion | Complete 29/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Moorooduc Primary School | 2327 | SEV | 2327_07 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  | Practical Completion | Complete 22/04/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Moriac Primary School | 4117 | SWV | 4117_07 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  | Practical Completion | Complete 6/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Morwell Central Primary School | 5568 | SEV | 5568_04 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  | Practical Completion | Complete 21/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Morwell Park Primary School | 4975 | SEV | 4975_07 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  | Practical Completion | Complete 21/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Mossgiel Park Primary School | 5205 | SEV | 5205_07 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects | Chippa | Construction Complete | Complete 29/01/2026 | Yes |  |  |  |  | failed final inspection, rectification eta? Clearance between handrail to be added to Performance Solution. | Yes |  |  |  | All works are completed. A site inspection and school acknowledgement will be sought from 1:1 Architects and Chippa. There is a six month defect liability period to cover any issues that may arise in this time. | Andrew - Final |  |  | Andrew | Aaron |  |  | lynn.ordish@education.vic.gov.au
| Mount Clear Primary School | 427 | SWV | 0427_06 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  | Practical Completion | Complete 29/07/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Mount Eliza Secondary College | 8102 | SEV | 8102_07 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  | Practical Completion | Complete 28/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Nar Nar Goon Primary School | 2248 | SEV | 2248_07 | PMP_OPO_Nov'23Bundle 19 | JMA Architects |  | Construction Complete | Complete 10/07/2024 | [10 empty] | Closed for Comms | NA
| Newington Primary School | 2103 | SWV | 2103_07 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  | Practical Completion | Complete 29/04/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Niddrie Primary School | 5410 | SWV | 5410_08 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  | Construction Complete | Complete 18/07/2024 | [10 empty] | Closed for Comms | NA
| Nossal High School | 8865 | SEV | 8865_05 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Hum | Construction Complete | complete 19/12/2025 | No | Yes |  | 2026-02-13 |  | Planter box lid variation and defect works to complete. 22/01 - Lid variation approved by Dileep/VSBA. Awaiting CFI with Hum. Defect inspections to be conducted thereafter 29/01 - Awaiting HUM program. 3/02 - Received Email from school (via Tim M) advising of final re-keying costs (~$13k). 05/02 - End of next week forecast completion 10/02 - Email received from school, Contractor illegal entry into school on Saturday (cut padlock), filled planter box & didn't address defects. 26/02 - Asphalt outstanding, school was thinking pit lid was also being done. | Yes |  | PDC - Raschid | Andrew | We understand that there are some defect and planter works to be completed, we are awaiting HUM program to complete these remaining works. Works are however expected to be completed by 16th February 2026. Please advise if this does not occur. |  | Joey | Andrew | Andrew |  | CFI inspection done but paperwork not received. Hum to chase. Variation of planter box before progressing defect rectification ($3k). Hum wont fix defects until variations done. CFI to be book indepently. | Problem site - HUM lost the master keys ($13k), illegal entry on Sat 7/02. | Joshua.Blanchard@education.vic.gov.au
| Overport Primary School | 4780 | SEV | 4780_05 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | Construction Complete |  | Yes | 2026-09-04 | yes | 2026-06-02 |  | Completed June. Bella to advise why PCC not yet issued - URGENT. Defects inspection not done | Yes |  |  | H&L | Works are completed and building surveyor has inspected with the CFI's expected iminently. H&L Architects and GRN Builder will contact the school to arrange a site walk and ensure defects are completed. School sign off will be sought and 6 months DLP will apply to the works. |  | Joey | requested GRN | Andrew |  |  |  | Julie.Gleeson@education.vic.gov.au |  | bella@hendersonandlodge.com.au; belinda.griffin@hendersonandlodge.com.au
| Pakenham Lakeside Primary School | 5504 | SEV | 5504_05 | PMP_OPO_Nov'23Bundle 19 | JMA Architects |  | Practical Completion | Complete 22/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Parktone Primary School | 4843 | SEV | 4843_06 | PMP_OPO_Nov'23Bundle 18 | JMA Architects |  | Practical Completion | Complete 8/10/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Parkwood Green Primary School | 5480 | SWV | 5480_06 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  | Practical Completion | Complete 15/09/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Patterson River Secondary College | 8725 | SEV | 8725_12 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN | Construction Complete |  | Yes | 2026-01-13 |  | 2026-06-02 |  | Work scope complete | Yes |  |  | H&L | Works are completed and building surveyor has inspected with the CFI's expected iminently. H&L Architects and GRN Builder will contact the school to arrange a site walk and ensure defects are completed. School sign off will be sought and 6 months DLP will apply to the works. |  | Joey | requested GRN | Andrew | Andrew |  |  | Peter.Friedl@education.vic.gov.au
| Pentland Primary School | 5369 | SWV | 5369_04 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  | Practical Completion | Complete 24/11/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA |  |  |  | Aaron
| Point Cook Senior Secondary College | 8847 | SWV | 8847_06 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  | Construction Complete | Complete 17/06/2024 | [10 empty] | Closed for Comms | NA
| Portland North Primary School | 1194 | SWV | 1194_07 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  | Practical Completion | Complete 18/09/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Portland Primary School | 489 | SWV | 0489_06 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  | Practical Completion | Complete 18/09/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Roslyn Primary School | 4663 | SWV | 4663_06 | PMP_OPO_Nov'23Bundle 16 | JMA Architects |  | Practical Completion | Complete 6/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Sandringham Primary School | 267 | SEV | 0267_07 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge |  | Practical Completion | Complete 23/07/2024 | NA |  |  |  |  | Removed from scope |  |  |  |  | Closed for Comms | NA
| Somerville Secondary College | 8875 | SEV | 8875_07 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  | Practical Completion | Complete 18/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Sorrento Primary School | 1090 | SEV | 1090_04 | PMP_OPO_Nov'23Bundle 15 | Spaces Pty Ltd |  | Practical Completion | Complete 31/07/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Springside Primary School | 8911 | SWV | 8911_04 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  | Practical Completion | Complete 20/03/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| St Albans East Primary School | 4741 | SWV | 4741_07 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  | Practical Completion | Complete 30/06/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| St Arnaud Primary School | 1646 | SWV | 1646_04 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd | Domain National |  | 16/2/2026 | [5 empty] | Hazardous Materials. December Holidays works commence 6th January 2026. program pending from Domain. | Yes |  |  |  | As advised, due to extreme heat and forecasted weather predicted to be over 35 degrees. Domain National will unfortunately not be on site at this stage until Monday 2nd February. Jordan and Alex will advise of any changes to the expceted completion dates. | Jordan has advised via email (30/1) to Melissa of the Monday 2nd recommencement. | Jordan | Jordan | Andrew | Aaron |  |  | melissa.mitchell@education.vic.gov.au | jennifer.gifford@education.vic.gov.au; shirlee.tillig@education.vic.gov.au | Jordan Veniamakis <jordan@himmelzimmer.com> | aaron@himmelzimmer.com; alex@domainnational.com.au; jamie@domainnational.com.au; tony.a@domainnational.com.au
| Tarneit Senior College | 8854 | SWV | 8854_07 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  | Practical Completion | Complete 29/07/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Teesdale Primary School | 2065 | SWV | 2065_08 | PMP_OPO_Nov'23Bundle 17 | Himmelzimmer Pty Ltd |  | Practical Completion | Complete 25/09/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Timbarra P-9 College | 5479 | SEV | 5479_08 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Hum |  | 27/02/2026 |  |  |  | 2026-03-13 |  | Ramp 15 TBC Expected PC 27/02/2026 (program to be submitted by Hum) 29/01 - Demo occurred today, pouring next week. Still tracking mid Feb 05/02 - R15 concrete pour done, handrails next week, 12/02 forecast completion 26/02 - Awaiting program to closeout. Small demo, removal handrails, removal concrete, pour and set, re-inspect. Hoping to finish by 7/03. | Yes |  | PDC - Raschid | Andrew | HUM and JMA Architects have advised Ramp 15 concrete pour was scheduled 30/01/2026 and completion is due by 12th February 2026. Please advise if this does not occur. |  | Joey | Andrew | Andrew | Andrew |  |  | Kyle.Sleep@education.vic.gov.au
| Toolern Vale and District Primary School | 5414 | SWV | 5414_08 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  | Practical Completion | Complete 31/07/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Toorak Primary School | 3016 | SEV | 3016_05 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd |  | Practical Completion | Complete 6/10/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Toorloo Arm Primary School | 3968 | SEV | 3968_07 | PMP_OPO_Nov'23Bundle 20 | Spaces Pty Ltd |  | Practical Completion | Complete 2/12/2025 | yes | yes | yes | yes |  |  | Yes |  |  |  | Closed for Comms | NA |  |  |  | Aaron
| Traralgon (Liddiard Road) Primary School | 4700 | SEV | 4700_08 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd | Jointly | Practical Completion | Complete 7/11/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Traralgon College (Ramps) | 8803 | SEV | 8803_07 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd | Jointly | Construction Complete |  | yes | yes | yes |  |  | waiting on school sign-off | Yes |  | Andrew - Final |  | Ramps and RFE works across East and West Campuses are forecast to be inspected for defects and sign off acknowledgement by the school on the 9th of February 2026. Noting there is a six month defect liability period to cover any issues within that time. Spaces architects have advised they have scheduled a site inspection on the 4th February 2026 to review progress. Please advise if this does not occur. | NA, recent email sent by Aaron 27/1 | Joey | Andrew | Andrew | Aaron |  |  | Claire.Gibson@education.vic.gov.au
* | Traralgon College (RFE) | 8804 | SEV | 8803_08 | PMP_OPO_Nov'23Bundle 22 | Spaces Pty Ltd | Jointly |  | 2026-02-09 | yes | yes | yes |  |  | Ramp work complete. RFE Roof December Holidays, The steel installation will occur between 5th and 23rd Jan 2026 exclusion zone required. Structural steel works are scheduled to occur between 8th January and 15th January 14/01 - PCC walkthru 9 Feb with School. CFI next week (hopefully) 21/01 - completion 6 Feb. Defects inspection 8 Feb 28/01 - New forecast 9 Feb. 04/02 - Still tracking. Awaiting Dileep approval for absestos removal (Jul 2025) 12/02 - Roof works completed yesterday | Yes |  | Andrew - Final |  | See above |  | Joey | Andrew | Andrew | Aaron
| Tulliallan Primary School | 5553 | SEV | 5553_03 | PMP_OPO_Nov'23Bundle 10 | 1:1 Architects |  | Practical Completion | Complete 20/10/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| University High School | 8405 | SWV | 8405_06 | PMP_OPO_Nov'23Bundle 11 | 1:1 Architects |  | Practical Completion | Complete 30/06/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Warragul Regional College | 8827 | SEV | 8827_07 | PMP_OPO_Nov'23Bundle 21 | Spaces Pty Ltd |  | Practical Completion | Complete 10/11/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Wendouree Primary School | 1813 | SWV | 1813_04 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects | Pirotta | Practical Completion | Complete 28/01/2026 | yes 28/01/26 | yes | yes |  |  | Ramps 2 and 1 Final inspection this week 21/01 - All works completedand currently safe to occupy. Ramp 3 CFI received 29/01 - Defects complete yesterday 28/01 | Yes |  |  |  | 1:1 Architects and Pirotta advised that all works are now completed, CFI has been recieved for all ramps and all ramps are open to the school. An inspection will be arranged for first week of February and school sign off acknowledgement will be sought noting that there is a six month defect liability period to cover any issues that may arise in this time. Please advise if this does not occur. | Andrew - Final | Cameron | Andrew | Andrew |  | CFI today 15/1. Ramp 1 & 2 PCC by 23 Jan |  | Christine.Branagh@education.vic.gov.au>
| Werribee Primary School | 649 | SWV | 0649_07 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects | Pirotta | Practical Completion | Complete 18/12/2025 | 23/01/2026 inspection | 2025-12-18 | yes |  |  | CFI received 18/12/2025 21/01 - defects rectification to be completed this week. cyclone fence scheduled 22/10 - Pirotta to provide temp fencing if cyclone fence not reworked. Fake turf between water tank lsab and new paving gap. FInal defects inspection by Friday. | Yes |  |  |  | 1:1 Architects and Pirotta advised that all works are now completed, CFI has been recieved for all ramps and all ramps are open to the school. An inspection will be arranged for first week of February and school sign off acknowledgement will be sought noting that there is a six month defect liability period to cover any issues that may arise in this time. Please advise if this does not occur. | Andrew - Final | Cameron | Andrew | Andrew | Aaron | CFI passed awaiting docs, defects done tmr (soon). Cyclone fence to be installed (this week or next). Pirotta to reach out and book inspection. |  | david.quinn@education.vic.gov.au
| Westall Secondary College | 8470 | SEV | 8470_10 | PMP_OPO_Nov'23Bundle 18 | JMA Architects | Ascots | Construction Complete | 2025-12-19 | Open | 2026-01-23 |  |  |  | Ramp 14 - non-DDA ramp, school request ramp over step to be treated as school defect. Will seek CFI with RBS to be issued next week | Yes |  |  |  | JMA advised that all scoped works have been completed. JMA to meet with the school regarding Ramp 14 Service Ramp for a solution. Please advise if this does not occur. |  | Joey |  | Andrew | Aaron | Build complete/ Defect inspection report done last week, to rectify before 27/1. Ramp 14 deviation sighted by school. | Wants updates | Lisa.LIU@education.vic.gov.au
| Williamstown High School | 8475 | SWV | 8475_10 | PMP_OPO_Nov'23Bundle 12 | 1:1 Architects |  | Practical Completion | Complete 6/08/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Woodlands Primary School | 5319 | SEV | 5319_08 | PMP_OPO_Nov'23Bundle 14 | Henderson and Lodge | GRN |  |  | Yes |  |  | 2026-06-02 |  | CFI expected this week | Yes |  | GRN - Drean | H&L | Works are completed and building surveyor has inspected with the CFI's expected iminently. H&L Architects and GRN Builder will contact the school to arrange a site walk and ensure defects are completed. School sign off will be sought and 6 months DLP will apply to the works. |  | Joey | requested GRN | Andrew | Andrew |  |  | Matthew.Amery@education.vic.gov.au
| Wyndham Vale Primary School | 5549 | SWV | 5549_05 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  | Practical Completion | Complete 29/07/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA
| Yarraman Oaks Primary School | 4807 | SEV | 4807_06 | PMP_OPO_Nov'23Bundle 19 | JMA Architects | Bowdens | Construction Complete | 2026-01-23 | Yes | 15/8/2025 for ramp works |  | 2026-01-30 |  | Covered way roof works completd. Defects inspection to be scheduled next week 26/02 - Asphalt work done yesterday. | Yes |  |  |  | JMA has advised that all works are completed and will seek sign off acknowledgement following the defect inspection the first week of February 2026. Noting that there is a six month defect liabiltiy period to cover any issues that may occur in this period. Please advise if this does not occur. |  | Joey |  | Andrew | Aaron | As updated |  | tina.ersch@education.vic.gov.au
| Yuille Park P-8 Community College | 5520 | SWV | 5520_04 | PMP_OPO_Nov'23Bundle 13 | 1:1 Architects |  | Practical Completion | Complete 29/07/2025 | yes | yes | yes | yes | [6 empty] | Closed for Comms | NA