Draft Scope Statement: School Maintenance Program Dashboard Proof of Concept

Purpose and Objectives

The purpose of this proof of concept (POC) is to develop a digital dashboard to support the delivery of a school maintenance compliance program (ramps program), improving visibility, coordination, and reporting across stakeholders.

Key Outcomes

- Reduce manual reporting effort across program and delivery teams

- Establish a single source of truth for delivery status

- Enable simple, role-appropriate reporting for all stakeholders

- Provide at-a-glance visibility of overall progress

- Deliver consistent and transparent progress metrics

Scope

In Scope

- Visualisation of schools, ramps, and their delivery status

- Ability to email stakeholders directly from the tool (or email client) with prefilled content

- Tracking of ramp-level lifecycle progress and milestones

- Core program metrics and progress indicators

- Ability for external organisations to view & update progress data

- Filtering and grouping of data

- Metrics dynamically recalculated based on filters/groupings

- Traffic light status for milestone delays

- Traffic light status for recency of school communication

Out of Scope

- Enterprise system integration (e.g. ERP, asset systems)

- Advanced scheduling or planning tools

- Advanced risk and cost management

Users and Stakeholders

Currently users can be grouped into three broad groups.

| Group | Examples | Needs |
| --- | --- | --- |
| Government / Client | Dept. of Education, VSBA, Ministerial | High-level progress, exceptions, reporting |
| End Users | School principals, facilities / maintenance managers | Status visibility, communication tracking/recipients |
| Delivery Teams | PMs, contractors, designers, surveyors, consultants | Update progress, manage milestones, track issues |

Functional Requirements & Features

User Access

- Multi organization secure access

- Delivery team access for data input, editing and update

- End users and Clients view only and generating reports

- Administrative users (PM team) with configuration and change control access.

Data input / Interaction

- Users can update ramp status, milestones, budget and free text fields

- Document and photo upload.

- Global search function

- Date search function

Communication

- Ability to send emails directly from the system, or link to email client with prepopulated information & addressees.

- Editable before sending.

- Last communication date with school should be captured

Progress Metrics

- % of ramps in each lifecycle stage (dial or pie chart)

- % of ramps achieving:

  - Practical Completion (dial or pie chart)

  - Administrative Completion (dial or pie chart)

- % of ramps with:

  - Identified defects (dial or pie chart)

  - Confirmed variations (dial or pie chart)

- Metrics dynamically calculated based on current filters/groupings.

Financial Metrics

- Budget vs actual vs forecast (at completion)

- Total variations

Filtering & Grouping

- Filter / sort by:

  - School / Region (if applicable)

  - Lifecycle stage

  - User defined fields (eg Priority, Flag fields

  - Status

- Support custom/user-defined fields

- Grouping & reporting via user fields.

- Metrics must recalculate dynamically based on filters / groupings

Information Requirements/Model

Hierarchy

The dashboard should support a hierarchical model: Program → School → Ramp

- A school may have multiple ramps

- A ramp is the primary unit of tracking

- Schools should have the ability to be grouped by region, priority, other fields.

Lifecycle Model

The following lifecycle stages are to be tracked for each ramp

- Design

- Construction

- Admin Closeout

- Defects Liability Period (DLP)

- Final Closure

Stage completion is defined by the corresponding milestone

Milestones

- Design Signoff

- Practical Completion

- Administrative Completion

- DLP Complete

- Final Closure

Planned and actual milestone dates

The system should allow flexibility to define interim milestones.

Admin Close Requirements

- Certificate of Final Inspection (CFI)

- School signoff

Risk/Delivery Signals

- Defects identified (Y/N or count)

- Variations confirmed (Y/N or count)

User / Additional fields

- Admin users have the ability to add free form fields

- Users can add from default field types

Dashboard Views / Visualisation

Program Overview / graphical metrics

- Total ramps and completion status

- Summary tiles and charts, could include

  - Dial / pie charts / burn down chart

  - % Practical Completion, % Admin Complete, Financial Performance

  - Overall communication metric/score

- Distribution across lifecycle stages

- Major metrics (completion, defects, variations, communication metric)

School View

- List/register of ramps with individual statuses

- Highlight of delayed or blocked ramps

- Communication history (last contact)

- Status field commentary update

- Schools or ramps “at risk”

- Issues, defects, variations

- Traffic light indicators for:

  - Late or at-risk milestones

  - Overdue or stale school communication

  - Financial / variation overruns (above 10%)

- Potential near or upcoming view (4 weeks / timeline view)

Could be two view or single view solution, the simpler the better. Could consider a ramp view (in future)

Data Considerations

- Data likely sourced from:

  - User, consultant, contractor manual inputs

  - Spreadsheets

- Expected update frequency: weekly (minimum)

- Data quality may vary across delivery partners

Non-Functional Expectations

- Simple, intuitive interface (minimal training required)

- Accessible via standard web browsers

- Suitable for both detailed users and executive stakeholders

POC Success Criteria

- Reduction in manual reporting

- Summary metrics & overall status within seconds

- Email functionality

- Demonstration of filtering and dynamic metrics

- Proving traffic light / at risk sites quickly

- Sample or real dataset

- Reduction in manual

Future Considerations

- Integration with enterprise systems

- Trending insights and advanced analytics

- Project and contractor performance insight

- Document and image management

- Workflow and approval process

- Mobile access